## excel
/Non Project/PSP Fundamentals & Advanced/Program 2
PSP1 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 39.4 | 31 | 30.5
Program Size
Base (B) | 109 | 109 | 109
Deleted (D) | 68 | 90 | 90
Modified (M) | 28 | 19 | 19
Added (A) | 130 | 131 | 241
Reused (R) | 0 | 0 | 0
Added and Modified (A+M) | 158 | 150 | 260
Total Size (T) | 171 | 150 | 260
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 158 | 259 | 259
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 07:45 PM el 20/02/2017